## Group member 1
TO-DO LIST
TO BE COMPLETED BY: |  | May 18th, 2025 |  | NAME: Bryan C. Weng Jiang
DEADLINE: |  | May 18th, 2025 |  | DATE: May 18th, 2025
PROJECT 2.5 PRESTIGE CARS
PERCENTAGE DONE | PHASE | START BY | ORIGINAL DUE BY | REVISED DUE BY | NUMBER(S) OF DAY(S) | REVISION NOTE(S)
100% | Planning | April 28th | May 17th | May 18th | 3 Weeks | 100% Completed
100% | Preparation | May 1st | May 7th | May 17th | 4 Days | 100% Completed
100% | Tables Normalization | May 9th | May 17th | May 17th | 8 Days | 100% Completed
100% | UDTs And Constraints | May 11th | May 17th | May 17th | 6 Days | 100% Completed
100% | Flattening Logic Finalized | May 13th | May 17th | May 17th | 4 Days | 100% Completed
100% | Views | May 17th | May 17th | May 17th | 1 Day | 100% Completed
100% | Paperwork/review and document summary | May 17th | May 17th | May 17th | 1 Day | 100% Completed
100% | Hand-off | May 18th | May 18th | May 18th | 1 Day | 100% Completed
100% | Follow-up | May 18th | May 18th | May 18th | 1 Day | Presentation and Integration

## Group member 2
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 3
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 4
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 5
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up