## Group #1
To do list for Project #2
To be completed by: |  | April 13th,2025 |  | Name: Group #1
Deadline: |  | April 13th,2025 |  | Date: 04/11/25
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Notes
100% | Assigning Work | 2025-04-11 |  |  | In a day | Jasky assigned work
100% | Overview of the Project | 2025-04-11 |  |  | In a day | Jasky summarized the project and made steps
100% | Created tables: UserAuthorization and WorkflowSteps | 2025-04-12 |  |  | In a day | Ashly created the tables
100% | Created procedure: TrackWorkFlow | 2025-04-12 |  |  | In a day | Ashly created the procedure
100% | Added 2 new tables: ProductCategory and Subcategory | 2025-04-12 |  |  | In a day | Ashly added the 2 new tables
100% | Alter every table to include 3 new columns, the userAuth keys, the date added, and the date of last update | 2025-04-12 |  |  | In a day | Ashly did
100% | Drop all pri keys and foreign key relations | 2025-04-12 |  |  | In a day | Ashly did
100% | Sequence Objects | 2025-04-12 |  |  | In a day | Jasky and David did
100% | Truncate tables | 2025-04-12 |  |  | In a day | Ashly did
100% | Create status function | 2025-04-13 |  |  | In a day | Jasky and David
100% | Meeting documentations | 2025-04-13 |  |  | 1 Day | Maitri did
100% | Created a PowerPoint that consists of two parts | 2025-04-13 |  |  | In a day | Ashly and David did
100% | First part of the PowerPoint | 2025-04-13 |  |  | In a day | William and Maitri did
100% | Create loading functions | 2025-04-13 |  |  | In a day | Ashly, David and Maitri did
100% | To do list | 2025-04-13 |  |  | In a day | William did
100% | Gantt Chart | 2025-04-13 |  |  | In a day | William did
100% | Parsing Objects | 2025-04-13 |  |  | In a day | David, Maitri and William
100% | Star schema | 2025-04-13 |  |  | In a day | Jasky and Richard
100% | Second part of the powerpoint | 2025-04-13 |  |  | In a day | Richard and Maitri did
100% | Recording | 2025-04-13 |  |  | In a day | Richard did
100% | Voice annotation | 2025-04-13 |  |  | In a day | Richard did

## Group member 4
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 5
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up