## Group member 2
To-do list
To be completed by: |  | Mar 21st, 2025 |  | Name: Richard Garnica & Jaskaran Bains
Deadline: |  | Mar 21st, 2025 |  | Date: 3/11/25
HW Chapter 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-03-11 | 2025-03-13 |  | 2 Days | Discussion + Getting on the same page
100% | Preparation | 2025-03-11 | 2025-03-13 |  | 2 Days
100% | SQL Exercises | 2025-03-13 | 2025-03-17 |  | 4 Days
100% | 10 Propositions | 2025-03-13 | 2025-03-20 | 2025-03-21 | 8 Days | Took longer than we expected
100% | Recording | 2025-03-21 | 2025-03-21 |  | 1 Day
100% | Submissions to Github | 2025-03-21 | 2025-03-21 |  | 1 Day