## Group member 1
To-do list
To be completed by: |  | Feb 14th, 2025 |  | Name: William Wang
Deadline: |  | Feb 14th, 2025 |  | Date: 02/01/25
HW Chapter 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-01-28 | 2025-01-29 | 2025-02-01 | 2 Days | Discussion
100% | Preparation | 2025-02-01 | 2025-02-02 |  | 1 Day
100% | Gantt Chart | 2025-02-02 | 2025-02-03 |  | 1 Day
100% | SQL Exercises | 2025-02-03 | 2025-02-04 |  | 1 Day
100% | 10 Propositions | 2025-02-04 | 2025-02-06 | 2025-02-14 | 10 Days | Took longer than we expected
100% | Recording | 2025-02-14 | 2025-02-14 |  | 1 Day
100% | Putting it up to Github | 2025-02-14 | 2025-02-14 |  | 1 Day
0%

## Group member 2
To-do list
To be completed by: |  | Feb 14th, 2025 |  | Name: Ashly Castillo & Jaskaran Bains
Deadline: |  | Feb 14th, 2025 |  | Date: 2/24/25
HW Chapter 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-02-24 | 2025-02-27 | 2025-02-28 | 4 Days | Discussion + Getting on the same page
100% | Preparation | 2025-02-28 | 2025-03-02 |  | 3 Days
100% | SQL Exercises | 2025-03-02 | 2025-03-06 | 2025-03-07 | 5 Days | Took longer than we expected
100% | 10 Propositions | 2025-03-02 | 2025-03-06 | 2025-03-07 | 4 Days | Took longer than we expected
100% | Recording | 2025-03-07 | 2025-03-07 |  | 1 Day
100% | Submissions to Github | 2025-03-07 | 2025-03-07 |  | 1 Day

## Group member 3
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 4
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 5
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up